## Tasks
1.1 | Agree on budget and event scope
1.2 | Fix a date and time for the event
1.3 | Anniversary date set
2.1 | GUESTS
2.1.1 | Make Guest list
2.1.2 | Send out invitations
2.1.3 | Finalize Guest list
2.1.4 | Number of guests confirmed
2.2 | RECEPTION VENUE
2.2.1 | Make reception venue short list
2.2.2 | Reception venue validated
2.2.3 | Book reception venue
2.3 | CATERING
2.3.1 | Make caterer short list
2.3.2 | Validate the caterer with management
2.3.3 | Plan food menu
2.4 | DECOR
2.4.1 | Create Anniversary logo design
2.4.2 | Print Anniversary banners
2.5 | ANIMATION
2.5.1 | Select and book DJ
2.5.2 | Select and book entertainment
2.5.3 | Create DJ Theme and Music
2.5.4 | Book Japanese-English interpreter
2.5.5 | Create Script of Japanese-English Translation
2.5.6 | Select and book audiovisual equipment
2.6 | GIFT
2.6.1 | Choose Gift type
2.6.2 | Design Original Gift
2.6.3 | Produce Original Gift
2.6.4 | Original Gift checked
2.7 | VIP GUESTS
2.7.1 | Select and book hotel rooms
2.7.2 | Select and book transport
2.8 | MEMORIES
2.8.1 | Select and book photographer
2.8.2 | Select and order a photo booth
3.1.1 | Bring all equipment to the venue
3.1.2 | Have a rehearsal
4 | Event day

## Resources
Resource Type | Resource ID | Resource Name | Standard Rate | Overtime Rate
Work | 1.1 | Project Manager | 140 | 40
Work | 1.2 | Logistics Manager | 120 | 40
Work | 1.3 | IT Manager | 100 | 40
Work | 1.3 | Logo Designer | 20 | 0
Work | 1.4 | Disc Jockey (DJ) | 40 | 20
Work | 1.5 | (JP-EN) Interpreter | 60 | 20
Work | 1.6 | Gift Designer | 20 | 0
Material | 2.1 | Reception Hall | 1000
Material | 2.2 | Banner | 200
Material | 2.3 | Audio/Visual Equipment | 150
Material | 2.4 | Gifts | 50
Cost | 3.1 | Catering Service | 2000
Cost | 3.2 | PhotoBooth Service | 500
Cost | 3.3 | Photography Service | 500
Cost | 3.4 | Hotel | 3000
Cost | 3.5 | Transportation Service | 1500
Notes: | 1. Assign per unit for Material Resources 2. All units are in dollar 3. Project Manager, Logistic Manger, IT Manager can be paid after the project is completed 4. Logo Designer, Disc Jockey, (JP-EN) Interpreter , Gift Designer, PhotoBooth Service, Photography Service can be paid as the tasks completion is in progress 5. The cost for Reception Hall, Banner, Audio/Visual Equipment, Gifts, Hotel Room, Catering Service, Transportation Service needs to paid in advance